## Sprint Overviews
TEAMS : | FRONTEND |  | BACKEND | DATABASE | UI/UX DESIGNERS |  | PROJECT MANAGER
Sprint 0 📅 Feb 1 - Feb 14 |  | Sprint 1 📅 Feb 15 - Feb 28 |  | Sprint 2 📅 March 1 - March 14 |  | Sprint 3 📅 March 15 - March 28
1. Project Setup Objective: Define scope, goals, and key requirements. Tasks: - Align objectives with the team. - Document core features (CRUD). - Set timelines and deadlines. |  | 1. User Registration & Login Mock-up Create a basic registration and login form. Add simple front-end validation (e.g., required fields). Display success/error messages (no backend yet). |  | 1. User Authentication (Registration & Login) Set up backend for user registration and login. Store user data in a database (MySQL/SQLite). Hash passwords and manage login sessions. |  | 1. UI Refinements Improve layout and responsiveness. Ensure consistency in fonts, colors, and spacing. Fix reported UI issues and enhance user experience.
|  | 2. Transaction Management Mock-up Design a form to enter transaction details (amount, description). Display transactions in a simple list (mock data, no database). Include a button to add transactions dynamically. |  | 2.Transaction Management (CRUD) Connect transaction form to the database. Implement Create, Read, Update, and Delete (CRUD) for transactions. |  | 2. Data Validation & Security Checks Strengthen form validations to prevent incorrect inputs. Check for security risks (SQL injection, XSS). Improve error handling for better user feedback.
2. Requirements Gathering Objective: Prepare the development environment. Tasks: Install required tools (IDE, version control, DBMS). Set up project repository (GitHub/Bitbucket). Configure local server and database (MySQL/SQLite).
|  | 3. Basic Dashboard Layout Create a dashboard with placeholders for user info & transactions. Add simple navigation to registration, login, and transaction pages. Ensure the design is clean and responsive. |  | 3. Session Handling Keep users logged in with session management. Add logout functionality. Ensure basic security (input validation, prepared statements). |  | 3. Final Testing & Review Conduct full system testing and fix critical issues. Ensure smooth workflow from login to transactions. Gather last-minute feedback and apply minor tweaks.
3. Design & Prototyping Objective: Define system architecture and structure. Tasks: Select architecture (client-server, API-based). Choose technologies (PHP, JavaScript, MySQL). Design database schema (users, transactions, income/expenses)
4. Project Review & Documentation Project Manager ensures all deliverables meet the initial objectives. UI/UX team finalizes any design inconsistencies. Document key takeaways for future improvements.
Figma Prototype :
https://www.figma.com/proto/Cc8Ae3h6nsKPCQs3aA9SLv/IPT?node-id=1-13&p=f&t=Nkvr98GGs0cwsfkj-1&scaling=scale-down&content-scaling=fixed&page-id=0%3A1&starting-point-node-id=1%3A13

## Test Cases
Login & Authentication Test Cases
Test Case No | Action | Inputs | Expected Output | Actual Output | Test Results | Comments
TC-01 | User enters valid login credentials | Username, Password | User is successfully logged in and redirected to the dashboard | Click Here!!
TC-02 | User logs out | Click "Logout" Button | User is logged out and redirected to the login page | Click Here!!
Registration Test Cases
Test Case No | Action | Inputs | Expected Output | Actual Output | Test Results | Comments
TC-01 | User enters valid registration details | Email, Password | User is successfully registered and redirected to login page | Click Here!!
Balance Management Test Cases
Test Case No | Action | Inputs | Expected Output | Actual Output | Test Results | Comments
TC-01 | User views account balance | Click "Balance" section | Shows Balance | Click Here!!
TC-02 | User adds a new card | Card Number, Expiry Date, CVV | Successfully added new Card | Click Here!!
TC-03 | User removes a card | Select Card, Click "Delete" | Successfully deleted Card | Click Here!!
TC -04 | User Views Card | Select Card | Shows Card Details | Click Here!!
Transaction Test Cases
Test Case No | Action | Inputs | Expected Output | Actual Output | Test Results | Comments
TC-01 | User adds a new transaction with valid inputs | SCNO, Branch, Full Name, Address, Phone No., Amount, Type | Transaction is successfully added and displayed in the list | Click Here!!
TC-02 | User deletes an existing transaction | Click "Delete Transaction" button | Transaction is removed from the list and database | Click Here!!
Bills Test Cases
Test Case No | Action | Inputs | Expected Output | Actual Output | Test Results | Comments
TC-01 | User adds a bill with valid inputs | User, Address, Billing Date, Amount, Payment Method (Card/Online) | Bill is successfully added and displayed in the list | Click Here!!
TC-02 | User selects "Card Payment" and enters valid card details | Card Number, Expiry, CVV | Bill is successfully added with card payment confirmation | Click Here!!
TC-03 | User selects "Online Payment" (PayPal) and logs in successfully | PayPal login credentials | Bill is added after successful authentication | Click Here!!
TC-004 | User deletes an existing bill | Click "Delete" on a bill | Bill is removed from the list | Click Here!!
Expenses Test Cases
Test Case No | Action | Inputs | Expected Output | Actual Output | Test Results | Comments
TC-01 | User adds a new expense entry | Expense Amount, Category, Date | Expense record is successfully added and displayed in the expense list | Click Here!!
TC-02 | User tries to add a new expense with missing fields | One or more fields left blank | Error message: "All fields are required" | Click Here!!
TC-03 | User enters an invalid expense amount | Amount contains letters/special characters | Error message: "Invalid amount. Please enter a valid number" | Click Here!!
TC-04 | User deletes an existing expense | Click "Delete" on an expense record | Expense record is successfully removed from the list | Click Here!!
TC-05 | User tries to delete a non-existing expense | Click "Delete" on a missing record | Error message: "Expense record not found" | Click Here!!
TC-06 | User cancels the deletion of an expense record | Click "Cancel" on the deletion confirmation | Expense record remains in the list | Click Here!!
TC-07 | User views the list of expenses | N/A | List of expenses is displayed correctly with details like amount, category, and date | Click Here!!
TC-08 | User tries to view expenses when there are none added | N/A | Message: "No expenses found" displayed | Click Here!!
Settings Test Cases
Test Case No | Action | Inputs | Expected Output | Actual Output | Test Results | Comments
TC-01 | User selects USD as the currency | USD selected from currency dropdown | Currency is set to USD and displayed correctly in the settings | Click Here!!
TC-02 | User selects PHP as the currency | PHP selected from currency dropdown | Currency is set to PHP and displayed correctly in the settings | Click Here!!
TC-03 | User tries to select an invalid currency | Invalid currency selected (e.g., not available in the list) | Error message: "Invalid currency selected" | Click Here!!
TC-04 | User enables Email notifications | Email toggle turned on | Email notifications are enabled and user is notified accordingly | Click Here!!
TC-05 | User disables Email notifications | Email toggle turned off | Email notifications are disabled and user no longer receives email alerts | Click Here!!
TC-06 | User enables SMS notifications | SMS toggle turned on | SMS notifications are enabled and user is notified via SMS | Click Here!!
TC-07 | User disables SMS notifications | SMS toggle turned off | SMS notifications are disabled and user no longer receives SMS alerts | Click Here!!
TC-08 | User enables In-App notifications | In-App toggle turned on | In-App notifications are enabled and user sees notifications within the app | Click Here!!
TC-09 | User disables In-App notifications | In-App toggle turned off | In-App notifications are disabled and user no longer receives in-app alerts | Click Here!!
TC-10 | User selects multiple notification methods (Email, SMS, In-App) | Email, SMS, and In-App toggles turned on | All selected notification methods are enabled, and user receives notifications accordingly | Click Here!!
TC-11 | User cancels notification settings changes | Click "Cancel" on notification settings | Notification settings remain unchanged | Click Here!!
Overview Test Cases
Test Case No | Action | Inputs | Expected Output | Actual Output | Test Results | Comments
TC-01 | User views the financial summary graph | N/A | Financial summary graph is displayed correctly, showing income, expenses, and balance | Click Here!!
TC-02 | User views the weekly financial summary | Select "Weekly" option | Weekly summary graph is displayed with data for the past week | Click Here!!
TC-03 | User views the monthly financial summary | Select "Monthly" option | Monthly summary graph is displayed with data for the current month | Click Here!!
TC-04 | User views the yearly financial summary | Select "Yearly" option | Yearly summary graph is displayed with data for the current year | Click Here!!
TC-05 | User views a short summary of recent expenses | N/A | A short list of recent expenses is displayed (e.g., last 5 expenses) | Click Here!!
TC-06 | User views a short summary of recent income | N/A | A short list of recent income is displayed (e.g., last 5 income entries) | Click Here!!
TC-07 | User generates a weekly financial report | Select "Generate Weekly Report" | Weekly financial report is generated, displayed, and user is prompted to export as PDF or DOC | Click Here!!
TC-08 | User generates a monthly financial report | Select "Generate Monthly Report" | Monthly financial report is generated, displayed, and user is prompted to export as PDF or DOC | Click Here!!
TC-09 | User generates a yearly financial report | Select "Generate Yearly Report" | Yearly financial report is generated, displayed, and user is prompted to export as PDF or DOC | Click Here!!
TC-10 | User selects to export the report in PDF | Select "Export as PDF" from the prompt | The report is successfully exported as a PDF file | Click Here!!
TC-11 | User selects to export the report in DOC | Select "Export as DOC" from the prompt | The report is successfully exported as a DOC file | Click Here!!
TC-12 | User cancels the export of the report | Click "Cancel" on the export prompt | Report is not exported, and the user returns to the overview screen | Click Here!!

## Test Cases Actual Output
Login & Authentication Test Cases |  | Login & Authentication Test Cases
Registration Test Cases
Balance Management Test Cases
Transaction Test Cases |  | Transaction Test Cases
Bills Test Cases |  | Bills Test Cases
Expenses Test Cases
Settings Test Cases
Overview Test Cases

## Agile Team And Roles
Project Team & Roles
Project Manager – Naruto Uzumaki 🍜🔥
Role: Leads the entire project, ensuring all teams work together, deadlines are met, and the final product meets expectations.
Responsibilities:
Sets project timelines and ensures smooth workflow.
Conducts stand-up meetings and resolves bottlenecks.
Oversees quality control and testing phases.
Communicates between stakeholders and developers.
Makes final decisions on priorities and changes.
Ensures that all deliverables align with project goals.
Frontend Team – BINI Members 🎤🎶 | UI/UX Designers – Straw Hat Pirates 🏴‍☠️🔥
Role: Responsible for building the user interface and ensuring a seamless user experience through responsive design and smooth interactions. | Role: Designs user-friendly interfaces and improves the overall user experience by focusing on navigation, visuals, and accessibility.
Members & Responsibilities: | Members & Responsibilities:
Aiah: Lead Frontend Developer – Oversees the frontend architecture and UI implementation. | Luffy (Lead Designer): Creates wireframes and high-level design concepts.
Colet: UI Components Specialist – Ensures the consistency of UI components across all pages. | Zoro: Works on user flow and navigation for seamless interactions.
Maloi: JavaScript & Interactivity – Adds animations and dynamic elements. | Sanji: Ensures color theory and typography balance.
Gwen: Mobile Optimization – Makes sure the UI is fully responsive. | Nami: Conducts user research and designs intuitive layouts.
Stacey: CSS & Styling – Works on the visual aesthetics and branding consistency. | Usopp: Works on animations and micro-interactions.
Jhoanna: Frontend Testing – Ensures all UI elements function correctly. | Robin: Focuses on accessibility and inclusive design.
Mikha: Accessibility & Performance – Optimizes speed and accessibility compliance. | Franky: Prototyping and A/B testing for UI performance.
Sheena: UI/UX Collaboration – Bridges the gap between UI/UX and frontend developers. | Chopper: Enhances mobile usability and touch-friendly elements.
Backend Team – LA Lakers 🏀🔥 | Database Team – Rappers (Kendrick Lamar & Legends) 🎤🔥
Role: Manages the logic, APIs, and security of the system, ensuring smooth data processing and authentication. | Role: Handles data storage, retrieval, security, and performance tuning for the system’s databases.
Members & Responsibilities: | Members & Responsibilities:
Kobe Bryant (Lead Backend Dev): Oversees the entire backend system and ensures performance. | Kendrick Lamar (Lead Database Admin): Designs the database schema and optimizes queries.
Shaquille O’Neal: Manages database interactions and query optimizations. | J. Cole: Ensures database normalization and indexing for better performance.
LeBron James: Ensures API security and authentication (e.g., JWT, OAuth). | Drake: Works on cloud database integration and backups.
Magic Johnson: Works on server-side business logic and efficiency. | Jay-Z: Manages data security, encryption, and access control.
Kareem Abdul-Jabbar: Develops robust RESTful APIs for seamless frontend-backend communication. | Eminem: Handles transaction management and data integrity.
Anthony Davis: Implements error handling and debugging strategies. | Travis Scott: Implements caching strategies for improved speed.
Meta World Peace: Monitors backend performance and optimizations. | Lil Wayne: Oversees database migrations and updates.
Austin Reaves: Works on user authentication and session handling. | Kanye West: Focuses on AI-driven database insights for analytics.

## Data Validation
Data Validation and Security Checks
Objective:
Ensure that all user inputs and system interactions are validated and secured to prevent errors, unauthorized access, and security vulnerabilities.
Description:
This feature enforces strict data validation across all forms and inputs, while also implementing security measures such as input sanitization, encryption, and protection against common threats like SQL Injection, XSS, and CSRF attacks.
✅ Tasks:
Implement frontend and backend validation for all user inputs.
Sanitize inputs to prevent SQL Injection and XSS attacks.
Ensure passwords are encrypted using hashing algorithms (e.g., bcrypt).
Implement CAPTCHA or reCAPTCHA to prevent bot submissions.
Enforce secure password policies (e.g., minimum length, special characters).
Implement token-based security (CSRF protection) for form submissions.
Secure API endpoints with authentication and role-based access control (RBAC).
📌 Priority: High
📌 Status: In Progress
📌 Sprint: Sprint 2
📌 Effort Estimation: Medium (3-5 days)
📌 Dependencies: User Authentication, Database Security, API Security
📌 Risks & Challenges:
Ensuring all inputs are correctly validated and sanitized.
Keeping security patches up to date against emerging threats.
📌 Acceptance Criteria:
All forms validate user input before submission.
Input sanitization prevents SQL Injection and XSS attacks.
Passwords are hashed before being stored in the database.
Unauthorized users cannot access restricted pages or actions.
🛠 Testing Plan:
Test form inputs with invalid and malicious data.
Verify password hashing and storage.
Simulate SQL Injection and XSS attacks to ensure protection.
Test role-based access control (RBAC) to restrict unauthorized actions.
🔍 Review & Approval: Approved By: [Team Lead / QA]
💡 Notes: Future updates can include two-factor authentication (2FA) for extra security and real-time monitoring of suspicious activities.

## Project Testing and Review
Final Testing and Project Review
Objective:
Ensure that the project is fully functional, meets all requirements, and is free from critical bugs before deployment.
Description:
This phase focuses on comprehensive testing of all features, UI components, security measures, and performance optimizations. It also includes a final review with stakeholders to confirm that all deliverables align with project goals.
✅ Tasks:
Conduct full system testing to verify all functionalities.
Perform UI/UX testing to ensure responsiveness and user-friendliness.
Run security checks for vulnerabilities (SQL Injection, XSS, CSRF, etc.).
Conduct performance testing to check for speed and scalability issues.
Perform cross-browser and cross-device testing for compatibility.
Carry out usability testing with test users to gather feedback.
Document any bugs or issues found and fix critical ones.
Prepare final project documentation for deployment.
Schedule and conduct project review meetings with stakeholders.
📌 Priority: High
📌 Status: In Progress
📌 Sprint: Final Sprint
📌 Effort Estimation: Large (1 week+)
📌 Dependencies: Completed Features, Security Measures, UI Refinements
📌 Risks & Challenges:
Identifying and fixing last-minute bugs.
Ensuring smooth performance under different conditions.
Addressing stakeholder feedback before final approval.
📌 Acceptance Criteria:
All core functionalities work as expected.
No major bugs or security vulnerabilities remain.
The system is fully responsive and works across different devices.
Final documentation is complete and accurate.
Stakeholders approve the project for deployment.
🛠 Testing Plan:
Conduct unit, integration, and system testing.
Simulate real-world scenarios to test reliability.
Perform load testing to check system stability.
Gather user feedback through usability testing.
🔍 Review & Approval: Approved By: [Team Lead / QA / Stakeholders]
💡 Notes: Any non-critical issues will be noted for future updates, and a post-launch monitoring plan should be in place.

## Session Handling
Session Handling
Objective:
Implement a secure and efficient session management system to track user activity and maintain authentication states.
Description:
This feature ensures that users remain logged in securely throughout their session and are logged out automatically when inactive or after a set time for security purposes.
✅ Tasks:
Implement session creation upon successful login.
Store user authentication data securely using session variables.
Set up automatic session expiration after a defined period of inactivity.
Implement session destruction upon user logout.
Display a session timeout warning before auto-logout.
📌 Priority: High
📌 Status: In Progress
📌 Sprint: Sprint 2
📌 Effort Estimation: Medium (3-5 days)
📌 Dependencies: User Authentication, Security Protocols
📌 Risks & Challenges:
Preventing session hijacking and unauthorized access.
Ensuring smooth session expiration handling without disrupting user experience.
📌 Acceptance Criteria:
Users remain logged in until they log out or the session expires.
Automatic logout after inactivity with a warning message.
Secure session storage to prevent unauthorized access.
🛠 Testing Plan:
Test session persistence across different browsers.
Verify auto-logout after the specified timeout period.
Check session destruction on manual logout.
🔍 Review & Approval: Approved By: [Team Lead / QA]
💡 Notes: Future updates can include "Remember Me" functionality for persistent logins and enhanced security features like multi-factor authentication (MFA).

## User Registration And Log in
User Login Form | User Authentication
Objective: Create a basic user login form. | Objective: Improve login security, validation, and user experience.
Description: Users log in with a username and password, with basic validation.
✅ Tasks:
✅ Tasks:
Add a "Forgot Password" link.
Create a login form with username & password fields. | Strengthen validation (e.g., enforce password length & complexity).
Add front-end validation. | Show detailed error messages for incorrect login attempts.
Show error/success messages. | Mock authentication flow with a success/error state.
Redirect to the dashboard (mock login, no backend). | Implement session handling for login persistence.
📌 Priority: High | 📌 Priority: High
📌 Status: In Progress | 📌 Status: In Progress
📌 Sprint: Sprint 1 | 📌 Sprint: Sprint 2
📌 Effort Estimation: Small (1-2 days) | 📌 Effort Estimation: Medium (3-5 days)
📌 Dependencies: UI Design, Frontend Setup | 📌 Dependencies: UI Design, Frontend Validation, Basic Authentication Logic
📌 Challenges: Validation errors, mobile responsiveness | 📌 Challenges: Prevent brute-force attacks, clear & helpful error messages
📌 Acceptance Criteria: | 📌 Acceptance Criteria:
Users can enter login details. | Users must enter valid credentials.
Required fields must be filled. | Error messages for incorrect/missing inputs.
Success message appears. | Successful login maintains user session.
🛠 Testing Plan: | 🛠 Testing Plan:
Check form validation for empty fields. | Test login with valid & invalid credentials.
Test success/error messages. | Verify error messages appear correctly.
Ensure mobile responsiveness. | Ensure secure login persistence.
Notes: Consider adding multi-factor authentication in future updates. | Notes: Consider adding two-factor authentication (2FA) and "Remember Me" for better security.
User Registration Form | User Registration Form
Objective: Create a basic user registration form. | Objective: Create a basic user registration form.
Description: Users can register with a username, email, and password, with basic validation. | Description: Users can register with a username, email, and password, with basic validation.
✅ Tasks: | ✅ Tasks:
Create a registration form with username, email, and password fields. | Create a registration form with username, email, and password fields.
Add front-end validation for required fields. | Add front-end validation for required fields.
Show error/success messages after submission. | Show error/success messages after submission.
Mock the registration by redirecting to the login page (no backend). | Mock the registration by redirecting to the login page (no backend).
📌 Priority: High | 📌 Priority: High
📌 Status: In Progress | 📌 Status: In Progress
📌 Sprint: Sprint 1 | 📌 Sprint: Sprint 1
📌 Effort Estimation: Small (1-2 days) | 📌 Effort Estimation: Small (1-2 days)
📌 Dependencies: UI Design, Frontend Setup | 📌 Dependencies: UI Design, Frontend Setup
📌 Challenges: Validation errors, ensuring smooth user experience | 📌 Challenges: Validation errors, ensuring smooth user experience
📌 Acceptance Criteria: | 📌 Acceptance Criteria:
Users can input a username, email, and password. | Users can input a username, email, and password.
All required fields must be filled before submission. | All required fields must be filled before submission.
Success message appears on successful registration. | Success message appears on successful registration.
🛠 Testing Plan: | 🛠 Testing Plan:
Check validation for empty fields. | Check validation for empty fields.
Test success/error message display. | Test success/error message display.
Ensure mobile responsiveness. | Ensure mobile responsiveness.
Notes: Consider adding email verification in future updates. | Notes: Consider adding email verification in future updates.

## Design and Prototyping
🛠️ Design & Prototyping Tools Figma – UI/UX design and prototyping Adobe XD – Alternative for UI/UX design Lucidchart / Miro – Wireframing, flowcharts, system diagrams Google Sheets – Budget planning, financial tracking | 🔔 Notifications Email Alerts (Transactional notifications) SMS Notifications (Optional, based on user settings)
Frontend (User Interface) React.js (Modern UI framework) Tailwind CSS (For styling) Chart.js / Recharts (For financial graphs & reports) Axios (For API calls) | ⚙️ Settings & Customization Currency Selection (USD, PHP, etc.) Language Preferences (English, Filipino, etc.) Notification Preferences (Email, SMS, both)
⚙️ Backend (Server-Side Logic) Node.js + Express.js (For handling API requests) JWT Authentication (For secure user login) MySQL / PostgreSQL (For structured financial data storage) MongoDB (For non-relational storage, optional) | 📂 Document & Collaboration Tools Google Docs/Sheets (For documentation and finance planning) GitHub / GitLab (Version control) Trello / Jira (Project management & tracking)
💰 Payment Integration Gcash / PayPal (For online payment tracking) | 🔹 Video Conferencing & Meetings Microsoft Teams – Video calls, meetings, and document collaboration Google Meet – Free and easy-to-use video conferencing Zoom – Best for large meetings and screen sharing Discord – Voice channels and casual team communication

## Transaction Management
Transaction Management Mock-up | Complete Transaction Management System (CRUD)
Objective: | Objective:
Design a basic transaction entry form and list display for users to input and view their transactions. | Finalize the transaction management functionality, allowing users to add, edit, and delete transactions with ease.
Description: | Description:
This feature provides a simple interface for adding, listing, and managing transactions without database integration. | This feature enables users to efficiently manage financial transactions by providing CRUD (Create, Read, Update, Delete) operations for transactions.
✅ Tasks: | ✅ Tasks:
Create a transaction entry form with fields (e.g., amount, description). | Polish the transaction form (ensure fields are validated and user-friendly).
Design a simple table/list to display transaction data dynamically. | Add mock “Edit” and “Delete” buttons for managing transactions.
Add basic styling for a clean user-friendly look. | Display transaction data with dynamic updates (after adding, editing, or deleting).
Implement a mock “Add Transaction” button to dynamically add transactions. | Refine the transaction list/table design for improved readability.
📌 Priority: High | 📌 Priority: High
📌 Status: In Progress | 📌 Status: In Progress
📌 Sprint: Sprint 1 | 📌 Sprint: Sprint 3
📌 Effort Estimation: Small (1-2 days) | 📌 Effort Estimation: Medium (3-5 days)
📌 Dependencies: UI Design, Frontend Setup, JavaScript for dynamic list updating | 📌 Dependencies: UI Design, Frontend Development, Data Management
📌 Risks & Challenges: | 📌 Risks & Challenges:
Ensuring proper validation for input fields. | Validating transaction inputs properly.
Maintaining a responsive and clean layout. | Ensuring seamless UI updates when transactions are modified.
Keeping the UI clear and responsive, even with multiple transactions.
📌 Acceptance Criteria:
📌 Acceptance Criteria:
Users can input transaction details (amount, description).
Transactions appear dynamically in a list upon submission. | Users can add new transactions with required fields.
The interface remains clear and structured. | Transactions can be edited or deleted dynamically.
The interface remains clear and easy to navigate.
🛠 Testing Plan:
🛠 Testing Plan:
Validate required fields (amount, description).
Ensure transactions appear correctly in the list. | Verify adding, editing, and deleting transactions.
Check UI responsiveness across different screen sizes. | Ensure UI updates correctly after each operation.
Check responsiveness across different devices.
🔍 Review & Approval: Approved By: [Team Lead / QA]
💡 Notes: Consider adding transaction categories in a future iteration. | 🔍 Review & Approval: Approved By: [Team Lead / QA]
💡 Notes: Consider integrating filtering and sorting features in future updates.

## UI Layout
Basic Dashboard Layout | UI Refinements
Objective: | Objective:
Design a simple and user-friendly dashboard layout for users to view and navigate essential features. | Enhance the user interface (UI) for better aesthetics, usability, and responsiveness.
Description: | Description:
This feature provides a structured dashboard interface that organizes key functionalities and displays relevant data in a visually appealing manner. | This feature improves the overall visual design and user experience by refining UI elements, ensuring consistency, and optimizing responsiveness.
✅ Tasks: | ✅ Tasks:
Create a navigation bar/sidebar for easy access to different sections (e.g., Transactions, Reports, Settings). | Improve color schemes, typography, and spacing for a cleaner look.
Design a main content area displaying key summaries (e.g., total balance, recent transactions). | Enhance button designs, form inputs, and icons for better usability.
Implement basic styling for a clean and responsive layout. | Optimize mobile responsiveness to ensure smooth user interaction on all devices.
Ensure mobile responsiveness for seamless usability. | Refine dashboard layout and component alignments for better readability.
📌 Priority: High | 📌 Priority: High
📌 Status: In Progress | 📌 Status: In Progress
📌 Sprint: Sprint 1 | 📌 Sprint: Sprint 2
📌 Effort Estimation: Small (1-2 days) | 📌 Effort Estimation: Medium (3-5 days)
📌 Dependencies: UI Design, Frontend Setup | 📌 Dependencies: Initial UI Design, Frontend Development
📌 Risks & Challenges: | 📌 Risks & Challenges:
Ensuring the layout remains intuitive for users. | Ensuring design consistency across different sections.
Maintaining a responsive design across different screen sizes. | Maintaining a balance between aesthetics and performance.
📌 Acceptance Criteria: | 📌 Acceptance Criteria:
Users can navigate easily between different sections. | UI elements are visually consistent across pages.
Dashboard displays key information clearly. | Buttons, forms, and navigation feel intuitive and user-friendly.
The interface maintains a modern and structured look. | The interface is responsive across desktop, tablet, and mobile.
🛠 Testing Plan: | 🛠 Testing Plan:
Verify navigation links work properly. | Verify UI improvements across different screen sizes.
Ensure dashboard widgets and sections display correctly. | Test navigation and interactive elements for smooth transitions.
Check responsiveness on different devices. | Ensure text, colors, and layouts adhere to design guidelines.
🔍 Review & Approval: Approved By: [Team Lead / QA] | 🔍 Review & Approval: Approved By: [Team Lead / QA]
💡 Notes: Consider adding charts, graphs, and widgets in future updates for better data visualization. | 💡 Notes: Consider adding dark mode and animations in future updates for a more dynamic experience.

## Project Setup
Gastos Tracker Pro Max (GT Pro Max) is a finance tracking system designed to help users monitor their income, expenses, transactions, and bills in a structured and visually appealing way. With an intuitive dashboard, categorized records, and customizable settings, users can gain better control over their personal or business finances. The system aims to simplify financial management by providing a seamless way to record, track, and analyze financial activities
📊 Dashboard – A real-time financial overview with visual graphs, recent transactions, and balance summaries.
Manual Data Entry – Transactions, expenses, and income must be manually recorded (no automatic bank sync).
⚙️ Settings & Preferences – Users can customize currency, update profile details, and modify system preferences.
💰 Transactions Management – Users can log, categorize, edit, and delete transactions, providing a structured way to track cash flow.
Limited Forecasting – While it provides summaries and insights, it does not have advanced financial forecasting tools.
Internet Dependency – Some functionalities may require an internet connection for updates and synchronization.
💳 Payments Management – Users can track payment histories, ensuring accurate financial records.
📄 Forms for Adding, Editing & Deleting Records – A streamlined way to input financial data, update existing entries, or remove outdated information.
No Multi-User Collaboration – Currently designed for individual use, not for teams or multi-user access.
📉 Expenses & Bills Tracker – A feature to record expenses, set reminders for due bills, and analyze spending habits.
Project Title: Gastos Tracker Pro Max
Description
Scope
Limitations

## Requirement Gathering
User Authentication & Access Control
Users can sign up, log in, and log out securely.
Performance Requirements
The system should support at least 100 concurrent users with optimal response times.
Transaction processing should not exceed 3 seconds to ensure a smooth user experience.
Reports and analytics should generate within 5 seconds even with large data.
Settings & Customization Currency Selection: Users can choose between Dollars ($), Pesos (₱)
Language Preferences: Supports multiple languages (English, Filipino, Spanish, etc.) and adjusts the UI accordingly.
Notification Preferences: Users can enable/disable notifications for:
  Email notifications (e.g., reports, alerts).
  SMS notifications (e.g., budget alerts, reminders).
  Push notifications (for mobile users).
Financial Reports & Data Export
Generate monthly, quarterly, and yearly financial reports.
Export reports in CSV, PDF, or Excel format.
Dashboard & Financial Overview
Displays total income, total expenses, balance summary.
Graphs and charts for financial insights.
Quick access to recent transactions.
Income & Expense Tracking
Users can log income and expenses with details (date, amount, category, description).
Ability to categorize transactions (Salary, Rent, Bills, Investments, etc.).
Security Requirements
All financial transactions must be encrypted using AES-256 and SSL/TLS.
User authentication should support MFA (Multi-Factor Authentication) for extra security.
Password hashing using bcrypt or Argon2.
Must comply with GDPR and data privacy laws regarding financial data storage.
Transaction Management
Add, edit, delete, and search transactions.
Filter transactions by category, date range, or amount.
Payment Users can link their bank accounts, e-wallets, or credit cards.
Secure bank-to-bank transfers for expenses and payments.
Support for multiple payment methods:
  Credit/Debit Cards (Visa, Mastercard)
  Digital Wallets (PayPal, GCash, PayMaya)
  Bank Transfers (Local and International)
Auto-categorization of transactions when payments are made.
Scheduled/Recurring Payments (e.g., monthly bills, subscriptions).
Regulatory Compliance
The system must adhere to GDPR, PCI-DSS, and local financial regulations to protect user financial data.
Tax calculation must comply with local tax laws when generating financial reports.
Scalability Requirements
The system should scale to support thousands of users with increasing transactions.
Cloud-based storage & database optimization for large financial records.
User Authentication Constraints
Multi-factor authentication (MFA) is required for handling sensitive financial transactions.
Failed login attempts trigger a temporary account lockout to prevent unauthorized access.
Payment Processing Constraints
Transaction processing time depends on third-party payment gateways (PayPal, Stripe, GCash, etc.).
Some payment methods may not be available in certain countries due to regional restrictions.
Currency exchange rates must be updated in real-time for accurate financial reporting.
Availability & Reliability
99.9% uptime to ensure continuous access to financial data.
Auto-save functionality to prevent data loss.
Offline mode to allow users to log expenses without an internet connection (syncs when online).
Usability & Accessibility
User-friendly UI optimized for both desktop and mobile devices.
Multi-language support (English, Tagalog, etc.).
Currency selection feature (USD, PHP, etc.), ensuring all reports and calculations adapt dynamically.
Dark & light mode customization for user preference.
Accessibility support for visually impaired users (text-to-speech, high contrast mode).
Data Storage Limitations
Sensitive financial data should be encrypted and cannot be stored indefinitely due to compliance requirements.
User data retention policies must follow privacy laws, allowing users to delete their financial records if requested.
Offline & Syncing Limitations
Offline mode allows logging expenses, but transactions will only sync when online.
Some features (like bank syncing) require an active internet connection and may have delays.
Functional Requirements
Non-functional Requirements
Constraints
Operational Hours & Customer Support
Support may only be available during business hours, leading to potential delays in resolving issues.
Real-time transaction updates depend on bank processing times and may not reflect immediately.

## Sprint Meetings
Sprint 0 Meetings | Sprint 1 Meetings | Sprint 2 Meetings | Sprint 3 Meetings
Day 1 ( Feb 1, 2024 ) | Day 1 | Day 1 | Day 1
Duration: 30 mins | Duration: 30 mins | Duration: 30 mins | Duration: 30 mins
Location: Google Meet | Location: Google Meet | Location: Google Meet | Location: Google Meet
Task: Project Kickoff & Objective Alignment | Task: Project Kickoff & Objective Alignment | Task: Sprint Planning | Task: Finalize User Registration and Login
Objective: Define project scope, goals, and introduce team roles. | Objective: Define project scope, goals, and introduce team roles. | Objective: Define sprint goals, assign tasks, and finalize timeline. | Objective: Finalize the user registration and login features for a polished experience.
Meeting Host: Naruto | Meeting Host: Naruto | Meeting Host: Naruto | Meeting Host: Naruto
Day 2 (Feb 2, 2024) | Day 2 | Day 2 | Day 2
Duration: 30 mins | Duration: 30 mins | Duration: 30 mins | Duration: 30 mins
Location: Google Meet | Location: Google Meet | Location: Google Meet | Location: Google Meet
Task: Core Feature Identification | Task: Core Feature Identification | Task: Improve User Registration Flow | Task: Complete Transaction Management System
Objective: Identify and document core features of the Bookkeeping/Finance Tracker system. | Objective: Identify and document core features of the Bookkeeping/Finance Tracker system. | Objective: Discuss and finalize registration form enhancements (e.g., validation, user feedback, UI updates). | Objective: Finalize the transaction management functionality, ensuring smooth interactions.
Meeting Host: Luffy (UI/UX Designer) | Meeting Host: Luffy (UI/UX Designer) | Meeting Host: Luffy (UI/UX Designer) | Meeting Host: Luffy (UI/UX Designer)
Day 3 (Feb 3, 2024) | Day 3 | Day 3 | Day 3
Duration: 30 mins | Duration: 30 mins | Duration: 30 mins | Duration: 30 mins
Location: Google Meet | Location: Google Meet | Location: Google Meet | Location: Google Meet
Task: Timeline & Deadline Planning | Task: Timeline & Deadline Planning | Task: Enhance User Login Flow | Task: Implement Dashboard Enhancements
Objective: Establish project timelines and key deadlines. | Objective: Establish project timelines and key deadlines. | Objective: Plan and implement dynamic error messages, mock login success, and improved validation. | Objective: Add final touches to the dashboard for a more complete user experience.
Meeting Host: Kobe (Backend Developer) | Meeting Host: Kobe (Backend Developer) | Meeting Host: Kobe (Backend Developer) | Meeting Host: Kobe (Backend Developer)
Day 4 | Day 4 | Day 4 | Day 4
Duration: 30 mins | Duration: 30 mins | Duration: 30 mins | Duration: 30 mins
Location: Google Meet | Location: Google Meet | Location: Google Meet | Location: Google Meet
Task: Development Environment Setup | Task: Development Environment Setup | Task: Mock-up Transaction CRUD Functionality | Task: Mock API Integration and Data Simulation
Objective: Ensure software and tools installation (IDE, version control, database). | Objective: Ensure software and tools installation (IDE, version control, database). | Objective: Plan and design the transaction management system with CRUD operations (mock interaction). | Objective: Simulate real-time data updates and API calls for a more realistic experience.
Meeting Host: Kobe | Meeting Host: Kobe | Meeting Host: Kobe | Meeting Host: Kobe
Day 5 | Day 5 | Day 5 | Day 5
Duration: 30 mins | Duration: 30 mins | Duration: 30 mins | Duration: 30 mins
Location: Google Meet | Location: Google Meet | Location: Google Meet | Location: Google Meet
Task: Repository Setup | Task: Repository Setup | Task: Dashboard Enhancements | Task: User Flow Testing and Refinement
Objective: Set up project repository on GitHub and configure access. | Objective: Set up project repository on GitHub and configure access. | Objective: Define UI updates, including transaction summaries and visual elements like charts. | Objective: Conduct user testing to ensure smooth navigation and functionality across the mock-up.
Meeting Host: Kendrick | Meeting Host: Kendrick | Meeting Host: Kendrick | Meeting Host: Kendrick
Day 6 | Day 6 | Day 6 | Day 6
Duration: 30 mins | Duration: 30 mins | Duration: 30 mins | Duration: 30 mins
Location: Google Meet | Location: Google Meet | Location: Google Meet | Location: Google Meet
Task: Server & Database Setup | Task: Server & Database Setup | Task: Simulate API Requests and Data Updates | Task: Sprint Review and Presentation
Objective: Establish local server and database (MySQL/SQLite) for development. | Objective: Establish local server and database (MySQL/SQLite) for development. | Objective: Implement mock API behavior with JSON responses for login, registration, and transactions. | Objective: Present the polished mock-up with core functionalities to stakeholders.
Meeting Host: Kobe (Backend Developer) | Meeting Host: Kobe (Backend Developer) | Meeting Host: Kobe (Backend Developer) | Meeting Host: Kobe (Backend Developer)
Day 7 | Day 7 | Day 7 | Day 7
Duration: 30 mins | Duration: 30 mins | Duration: 30 mins | Duration: 30 mins
Location: Google Meet | Location: Google Meet | Location: Google Meet | Location: Google Meet
Task: System Architecture Planning | Task: System Architecture Planning | Task: User Interaction Testing | Task: Sprint Retrospective
Objective: Decide on overall architecture (client-server, API-based). | Objective: Decide on overall architecture (client-server, API-based). | Objective: Gather feedback from mock users on the registration, login, and transaction process. | Objective: Review the sprint, identify lessons learned, and plan for Sprint 4.
Meeting Host: Aiah | Meeting Host: Aiah | Meeting Host: Aiah | Meeting Host: Aiah
Day 8 | Day 8 | Day 8 | Day 8
Duration: 30 mins | Duration: 30 mins | Duration: 30 mins | Duration: 30 mins
Location: Google Meet | Location: Google Meet | Location: Google Meet | Location: Google Meet
Task: Technology Stack Finalization | Task: Technology Stack Finalization | Task: Sprint Review and Demo | Task: Adjustments & Finalization
Objective: Choose key technologies (PHP, JavaScript, MySQL). | Objective: Choose key technologies (PHP, JavaScript, MySQL). | Objective: Showcase the updated mock-up with new features to stakeholders and collect feedback. | Objective: Apply feedback from stakeholders and finalize remaining Sprint 3 tasks.
Meeting Host: Luffy | Meeting Host: Luffy | Meeting Host: Luffy | Meeting Host: Luffy
Day 9 | Day 9 | Day 9 | Day 9
Duration: 30 mins | Duration: 30 mins | Duration: 30 mins | Duration: 30 mins
Location: Google Meet | Location: Google Meet | Location: Google Meet | Location: Google Meet
Task: Database Schema Design | Task: Database Schema Design | Task: Sprint Retrospective | Task: Code Refinement and Optimization
Objective: Design database schema with tables for users, transactions, income/expenses. | Objective: Design database schema with tables for users, transactions, income/expenses. | Objective: Reflect on Sprint 2, discuss challenges, and document improvements for Sprint 3. | Objective: Optimize code, fix bugs, and ensure efficiency before the next sprint.
Meeting Host: Kendrick | Meeting Host: Kendrick | Meeting Host: Kendrick | Meeting Host: Kendrick
Day 10 | Day 10 | Day 10 | Day 10
Duration: 30 mins | Duration: 30 mins | Duration: 30 mins | Duration: 30 mins
Location: Google Meet | Location: Google Meet | Location: Google Meet | Location: Google Meet
Task: Review & Wrap-up | Task: Review & Wrap-up | Task: Adjustments & Finalization | Task: Final Sprint Planning for Sprint 4
Objective: Review sprint progress, address blockers, and finalize Sprint 0 activities. | Objective: Review sprint progress, address blockers, and finalize Sprint 0 activities. | Objective: Apply quick fixes based on Sprint 2 feedback, finalize changes, and prepare backlog for Sprint 3. | Objective: Prepare backlog, define Sprint 4 objectives, and align team expectations.
Meeting Host: Naruto | Meeting Host: Naruto | Meeting Host: Naruto | Meeting Host: Naruto